# GroundUp AI — Comprehensive Implementation Plan

### End-to-End Build Plan for the AI-Powered Construction Financial Control Web Application

This document is the master implementation plan. It assumes the reader has the Architecture Plan and the Expense-Tracking/Live-Status Spec already produced, and takes them to implementation-ready detail: repo structure, every module’s endpoints, every frontend page/component, the full sprint-by-sprint schedule, environment setup, DevOps pipeline, security checklist, testing pyramid, cost model, and risk register. Nothing below is left as “TBD” without an explicit owner and target sprint.

## Table of Contents

- Executive Summary

- Repository & Environment Setup

- Database Implementation Plan

- Backend Implementation — Module by Module

- Document Intelligence Pipeline — Implementation Detail

- Financial Calculation & Alerting Engine — Implementation Detail

- Frontend Implementation — Page by Page

- Auth & Security Implementation Checklist

- DevOps, Infrastructure & CI/CD

- Testing Strategy — Full Pyramid

- Sprint-by-Sprint Roadmap (24 Weeks)

- Team, Roles & RACI

- Cost Model

- Risk Register

- Definition of Done / Pilot-Launch Checklist

- Post-V1 Roadmap (V1.1+)

- Appendix: Mapping to Reference Screens

## 1. Executive Summary

Product: GroundUp AI — ingests messy construction documents (invoices, receipts, permits, bank slips), extracts data via OCR+LLM, and maintains four continuously reconciled Truths (Budget, Spend, Funding, Progress) so a developer always knows their Net Cash Exposure and whether the project is on track (cost and schedule).

Delivery model: Modular monolith (FastAPI) + Next.js frontend + async document pipeline (Textract/Claude) + Postgres/S3, deployed on AWS. Team of 7–9. 24-week V1, then V1.1.

This plan’s structure:

- §2 Repository & environment setup

- §3 Database implementation (full DDL plan)

- §4 Backend module-by-module implementation (every endpoint)

- §5 Document Intelligence pipeline implementation

- §6 Financial calculation & alerting engine implementation

- §7 Frontend implementation (every page/component)

- §8 Auth & security implementation

- §9 DevOps, infrastructure, CI/CD

- §10 Testing strategy (full pyramid)

- §11 Sprint-by-sprint roadmap (24 weeks, week-level detail)

- §12 Team, roles, RACI

- §13 Cost model (build + run)

- §14 Risk register

- §15 Definition of Done / launch checklist

- §16 Post-V1 roadmap (V1.1+)

## 2. Repository & Environment Setup

### 2.1 Repository structure (monorepo, recommended)

groundup-ai/
├── apps/
│   ├── web/                     # Next.js frontend
│   │   ├── app/                 # App Router pages
│   │   ├── components/
│   │   ├── lib/                 # API client, auth helpers
│   │   ├── hooks/
│   │   └── styles/
│   └── api/                     # FastAPI backend
│       ├── app/
│       │   ├── main.py
│       │   ├── core/             # config, security, db session
│       │   ├── modules/
│       │   │   ├── projects/
│       │   │   ├── financial/
│       │   │   ├── documents/
│       │   │   ├── reconciliation/
│       │   │   ├── draws/
│       │   │   ├── reporting/
│       │   │   └── alerts/
│       │   ├── workers/          # queue consumers (pipeline steps)
│       │   ├── ai/               # LLM prompt templates, client wrapper
│       │   └── db/
│       │       ├── models/
│       │       └── migrations/   # Alembic
│       └── tests/
├── packages/
│   ├── shared-types/             # OpenAPI-generated TS types shared with web
│   └── ui/                       # shared design-system components
├── infra/
│   ├── terraform/                # AWS IaC
│   └── docker/
├── .github/workflows/            # CI/CD
└── docs/

Why monorepo: the frontend consumes a fast-evolving API; generating shared TS types from FastAPI’s OpenAPI schema on every backend change (via openapi-typescript) is trivial in a monorepo and eliminates an entire class of integration bugs.

### 2.2 Core tooling to install/configure at project kickoff

| Tool | Purpose | Setup task |
| --- | --- | --- |
| Python 3.12 + Poetry | Backend dependency management | poetry init, lock file committed |
| Node 20 + pnpm | Frontend dependency management | pnpm-workspace.yaml for monorepo |
| Docker + Docker Compose | Local dev parity (Postgres, Redis) | docker-compose.dev.yml with Postgres 16, Redis 7 |
| Alembic | DB migrations | alembic init, wired to SQLAlchemy models |
| pre-commit | Lint/format gate | ruff, black, mypy (backend); eslint, prettier (frontend) |
| GitHub Actions | CI/CD | see §9 |
| Terraform | AWS infra as code | modules for RDS, S3, SQS, ECS/Fargate, VPC |
| 1Password/Vault or AWS Secrets Manager | Secrets | no secrets in .env committed, ever |

### 2.3 Environment variables (baseline — expand per module)

DATABASE_URL=
REDIS_URL=
S3_BUCKET_DOCUMENTS=
AWS_REGION=
TEXTRACT_ROLE_ARN=
ANTHROPIC_API_KEY=
JWT_SECRET / JWT_PUBLIC_KEY
WORKOS_API_KEY / AUTH0_DOMAIN
SENTRY_DSN
NEXT_PUBLIC_API_BASE_URL

## 3. Database Implementation Plan

### 3.1 Migration sequencing (Alembic revisions, in build order)

- 0001_orgs_users — organizations, users

- 0002_projects — projects, investor_contributions, project_milestones

- 0003_budget — budget_lines, change_orders

- 0004_documents — documents (with file_hash, S3 pointers)

- 0005_invoices_expenses — invoices, expenses

- 0006_accounting — accounting_transactions, reconciliation_matches

- 0007_progress — inspections, progress_records

- 0008_draws — draws, draw_lines, lender_decisions, disbursements

- 0009_audit — audit_events (append-only; revoke UPDATE/DELETE grants in the same migration)

- 0010_financial_status — financial_status_snapshots, spend_categories, alerts (from the tracking spec)

- 0011_rls_policies — enable RLS + policy per tenant-scoped table (separate migration so it’s independently reviewable/auditable)

### 3.2 Row-Level Security implementation detail

ALTER TABLE budget_lines ENABLE ROW LEVEL SECURITY;
CREATE POLICY tenant_isolation ON budget_lines
  USING (project_id IN (
    SELECT id FROM projects WHERE org_id = current_setting('app.current_org_id')::uuid
  ));

- Set via FastAPI DB-session dependency: SET LOCAL app.current_org_id = :org_id at the start of every request transaction, sourced from the validated JWT claim — never from a request body/query param.

- Task: write an automated test suite that, for every tenant-scoped table, attempts a cross-org read/write and asserts it fails, run in CI on every migration change.

### 3.3 Audit log implementation

- Every mutating service-layer function wraps its DB write in: begin tx → perform write → insert audit_events row (actor, entity, action, prev_state, new_state) → commit.

- Implemented as a reusable @audited decorator/context manager in app/core/audit.py so engineers can’t forget it on a new endpoint — code review checklist item (§15) enforces this.

### 3.4 Materialized/snapshot computation

- financial_status_snapshots populated by a service function recompute_snapshot(project_id), called synchronously after: expense verified, disbursement cleared, inspection passed, change order approved.

- For V1 scale, synchronous recompute (sub-100ms with proper indexes) is fine; if snapshot computation later becomes a bottleneck, move to an async queue trigger — build the function so this swap requires no interface change (same function signature, just invoked differently).

## 4. Backend Implementation — Module by Module (Full Endpoint List)

### 4.1 Auth Module

POST /auth/login                  (email/password)
POST /auth/sso/callback           (SSO/magic-link callback)
POST /auth/refresh
POST /auth/logout
GET  /auth/me

### 4.2 Organizations & Users

POST /orgs                        (create org — new-user intake flow, image 1)
GET  /orgs/{id}
POST /orgs/{id}/invite
GET  /orgs/{id}/users
PATCH /users/{id}/role

### 4.3 Projects Module

POST /projects                              (Mode A: Greenfield / Mode B: In-Flight)
GET  /projects                              (portfolio list — image 2)
GET  /projects/{id}
PATCH /projects/{id}
POST /projects/{id}/milestones
GET  /projects/{id}/milestones
PATCH /milestones/{id}
POST /projects/{id}/investors
GET  /projects/{id}/investors

### 4.4 Financial Module (Budget Truth)

POST /projects/{id}/budget-lines            (bulk create from parsed SOV)
GET  /projects/{id}/budget-lines
PATCH /budget-lines/{id}
POST /budget-lines/{id}/change-orders
POST /projects/{id}/budget/lock              (Lock Budget Truth V1 — role-gated: Owner/Finance Lead only)

### 4.5 Documents Module

POST /projects/{id}/documents/presign        (get S3 presigned upload URL)
POST /projects/{id}/documents                (register uploaded doc, triggers pipeline)
GET  /projects/{id}/documents?status=
GET  /documents/{id}
GET  /documents/{id}/download-url
PATCH /documents/{id}/verify                 (human split-screen correction + confirm)

### 4.6 Expenses / Invoices (Spend Truth)

GET  /projects/{id}/expenses?status=VERIFIED|PENDING
GET  /projects/{id}/invoices
PATCH /invoices/{id}                          (manual correction pre-verification)
POST /invoices/{id}/mark-duplicate

### 4.7 Reconciliation Module

GET  /projects/{id}/reconciliation/exceptions
POST /reconciliation/matches/{id}/confirm
POST /reconciliation/matches/{id}/reject

### 4.8 Draws Module

POST /projects/{id}/draws                     (create draft draw)
GET  /projects/{id}/draws
GET  /draws/{id}
POST /draws/{id}/readiness-check               (4-point pre-flight gate)
POST /draws/{id}/line-items
POST /draws/{id}/submit                        ("Submit to Heritage Bank" — image 3)
POST /draws/{id}/lender-decision                (full/partial/rejected)
POST /draws/{id}/disbursement                   (record cleared wire)
GET  /draws/{id}/revisions                      (child draws via parent_draw_id)

### 4.9 Financial Status Module (from tracking spec)

GET  /projects/{id}/financial-status
GET  /projects/{id}/financial-status/history
GET  /projects/{id}/spend-breakdown?by=trade|vendor|week
GET  /projects/{id}/alerts?status=open
POST /alerts/{id}/resolve

### 4.10 Reporting Module

GET  /projects/{id}/reports/investor-summary
GET  /orgs/{id}/reports/portfolio-rollup
POST /projects/{id}/reports/export             (PDF/Excel export job)

### 4.11 AI Assistant / “Ask AI Analyst” (seen in images 2 & 3)

POST /projects/{id}/ai/ask                      (chat-style Q&A grounded in project data)
GET  /projects/{id}/ai/weekly-brief

Implementation note: this endpoint retrieves the relevant structured data (snapshot, open alerts, recent documents) server-side, injects it into a constrained prompt, and returns the LLM’s natural-language answer — the LLM never queries the database directly.

## 5. Document Intelligence Pipeline — Implementation Detail

### 5.1 Worker architecture

- Queue: AWS SQS (three queues: ingest, extract, review-notify) or a single Temporal workflow per document if adopting Temporal (recommended for visibility into stuck documents).

- Each pipeline step (§4.6.1 of the architecture plan) is an idempotent worker function — safe to retry without double-posting an expense (enforce via a unique constraint on documents.id + step name in a pipeline_steps log table).

### 5.2 New supporting table

CREATE TABLE pipeline_steps (
  id UUID PRIMARY KEY,
  document_id UUID REFERENCES documents(id),
  step_name TEXT,             -- 'classify' | 'ocr' | 'llm_extract' | 'normalize' | 'validate' | 'match'
  status TEXT,                -- 'PENDING' | 'RUNNING' | 'DONE' | 'FAILED'
  output JSONB,
  confidence NUMERIC,
  started_at TIMESTAMPTZ,
  completed_at TIMESTAMPTZ,
  UNIQUE(document_id, step_name)
);

This gives full observability (“this invoice is stuck at llm_extract, retried 3 times”) — critical for support/debugging and for the “PHOTO ANALYSIS” style confidence badges seen in image 3.

### 5.3 Implementation steps, in build order

- Build ocr_service.py — wraps Textract AnalyzeExpense/AnalyzeDocument API, returns normalized field/confidence dict.

- Build llm_extract_service.py — Claude client wrapper with a strict JSON schema per document type (invoice schema, SOV schema, inspection-card schema); Pydantic-validates every response; on schema-validation failure, auto-route to Needs_Review rather than retry-loop indefinitely.

- Build normalize_service.py — currency/date parsing, vendor canonicalization against a vendors lookup table (fuzzy-matched, human-confirmable on first sight of a new vendor name).

- Build duplicate_service.py — RapidFuzz scoring across vendor+amount+date window; writes candidate matches to reconciliation_matches.

- Build matching_service.py — links a verified expense to the correct budget_line via cost-code suggestion (LLM-assisted) + human confirmation.

- Wire the queue consumers to call these services in sequence, writing to pipeline_steps after each, and updating documents.status per the state machine.

- Build the split-screen review UI (frontend, §7) against PATCH /documents/{id}/verify.

### 5.4 Cost & performance controls

- Send Textract’s extracted text, not the raw image, to Claude wherever possible — materially cheaper per document and faster.

- Cache canonical vendor names/cost-code mappings so repeat vendors skip the LLM classification step entirely after the first occurrence (deterministic lookup instead).

- Batch the weekly AI brief generation as a single scheduled job across all active projects rather than per-request generation.

## 6. Financial Calculation & Alerting Engine — Implementation Detail

(Full formulas already specified in the Expense-Tracking spec — this section is the build plan for that spec.)

- financial_engine/truths.py — pure functions: compute_bt(), compute_st(), compute_ft(), compute_gf(). Unit-tested against hand-built fixtures (this is the single most safety-critical file in the codebase — 100% branch coverage required).

- financial_engine/evm.py — compute_cpi(), compute_spi(), compute_eac(), classify_status() (returns ON_TRACK/OVER_BUDGET/BEHIND_SCHEDULE/AT_RISK).

- financial_engine/snapshot_service.py — orchestrates the above, writes financial_status_snapshots. Called from the relevant domain-service write paths (§3.4).

- alerts/rules_engine.py — the 7 deterministic rules from the tracking spec, each a pure function (snapshot, budget_lines) -> Optional[AlertCandidate]; evaluated after every snapshot write; opens/auto-resolves alerts rows.

- ai/explain_alert.py — async job, called after an alert opens, generates the human-readable alerts.message via a constrained Claude prompt (numbers-in, explanation-out only — see AI-boundary table in the tracking spec).

## 7. Frontend Implementation — Page by Page

| Route | Purpose | Key components | Data hooks |
| --- | --- | --- | --- |
| /login | Auth (matches image 1) | SSOButton, CredentialsForm, AccessTypeToggle | useAuth() |
| /onboarding/[step] | 6-phase wizard (PRD §5) | WizardStepper, SOVUploader, ColumnMappingDrawer, BudgetLockConfirm | useOnboardingState() (persisted draft, SETUP_DRAFT resume) |
| /portfolio | Dashboard (image 2) | FourTruthsTileRow, AIWeeklyBrief, ProjectGrid/TimelineToggle, AskAIAnalyst (floating) | useFinancialStatus(), useAlerts() |
| /projects/[id] | Project detail | StatusBadge (CPI/SPI), SpendBreakdownChart, BudgetVsSpendBar | useProject(), useSpendBreakdown() |
| /projects/[id]/draws | Draw list | DrawTable, severity badges | useDraws() |
| /projects/[id]/draws/[drawId] | 4-step draw wizard (image 3: Site progress → Receipts & matching → Line items → Lender package) | SitePhotoGrid (with AI-match %), SplitScreenReviewer, PreflightChecklist, SubmitToLenderButton | useDraw(), useReadinessCheck() |
| /projects/[id]/documents | Ingestion inbox | DocumentQueueTable (status pills matching the state machine), SplitScreenReviewer (shared component with draws) | useDocuments() |
| /projects/[id]/expenses | Verified ledger (§4 of tracking spec) | ExpenseTable, filters | useExpenses() |
| /projects/[id]/reports | Investor/portfolio reports | ReportExportButton | useReports() |
| /projects/[id]/alerts | Alerts panel | AlertList (severity-colored), ResolveButton | useAlerts() |
| /settings/org | Org/role management | TeamTable, RoleSelector | useOrgUsers() |
| /settings/project/[id] | Lender terms, retainage config | LenderTermsForm | useProjectSettings() |

Shared component library (packages/ui): StatusBadge, ConfidenceChip (the “98% AI match” badges in image 3), SourceLinkIcon (click-to-source), Sparkline, SeverityPill.

Real-time layer: a single WebSocket connection per authenticated session, subscribed to project:{id}:updates; backend publishes on document status change, new alert, and snapshot recompute — drives live badge updates without polling (matches the “AI verified framing milestone” instant-feedback UX in image 3).

## 8. Auth & Security Implementation Checklist

- ☐ JWT access token (15 min) + refresh token (7 days, rotated) via WorkOS/Auth0

- ☐ Role/permission matrix enforced via FastAPI dependency (require_role("OWNER", "FINANCE_LEAD")) on every mutating route

- ☐ RLS enabled + tested on every tenant-scoped table (§3.2)

- ☐ All S3 objects private, accessed only via short-lived presigned URLs

- ☐ Secrets in AWS Secrets Manager, injected at deploy time, never in source

- ☐ TLS everywhere (ALB termination + internal service mesh if split later)

- ☐ Input validation via Pydantic on every endpoint (rejects malformed financial payloads before they reach the DB)

- ☐ Rate limiting on auth endpoints (Redis-backed)

- ☐ Dependency scanning (Dependabot + pip-audit/npm audit) in CI

- ☐ OWASP Top-10 review pass before pilot launch

- ☐ Audit log immutability enforced at DB grant level (no UPDATE/DELETE on audit_events)

## 9. DevOps, Infrastructure & CI/CD

### 9.1 AWS infrastructure (Terraform modules)

- VPC with private subnets for RDS/workers, public subnet for ALB

- RDS Postgres 16 (Multi-AZ from Phase 5 onward)

- S3 bucket (groundup-documents-{env}), versioning + SSE-KMS

- SQS queues (or Temporal Cloud namespace)

- ECS Fargate services: api, worker, scheduled tasks (snapshot/alert cron if not event-driven)

- ElastiCache Redis

- CloudFront + S3 for the Next.js static assets (or Vercel for frontend hosting — simpler initial choice, migrate to self-hosted only if needed)

- Secrets Manager, CloudWatch log groups, X-Ray or OpenTelemetry collector

### 9.2 CI/CD pipeline stages (GitHub Actions)

on: pull_request
  1. lint (ruff/eslint)
  2. type-check (mypy/tsc)
  3. unit tests (pytest / vitest)
  4. migration dry-run against ephemeral Postgres
  5. build docker images

on: merge to main
  6. deploy to staging (Terraform apply + ECS deploy)
  7. run integration/E2E suite (Playwright) against staging
  8. manual approval gate
  9. deploy to production

### 9.3 Environments

local (docker-compose) → staging (full AWS, seeded with synthetic 161 Woodlawn Ave / 532 Palacsite data) → production.

## 10. Testing Strategy — Full Pyramid

| Layer | Tooling | Coverage target | Focus |
| --- | --- | --- | --- |
| Unit | pytest (backend), vitest (frontend) | ≥90% on financial_engine/* | Truths/CPI/SPI/EAC formulas, alert rules |
| Integration | pytest + testcontainers (real Postgres) | All API endpoints | RLS isolation, state-machine transitions, audit-log writes |
| Pipeline golden-set | Custom harness | Fixed sample doc set | OCR+LLM extraction accuracy regression detection on every prompt change |
| Contract | OpenAPI schema diff in CI | 100% | Prevents breaking frontend/backend contract silently |
| E2E | Playwright | Critical paths (onboarding, upload→verify→post, draw submission) | Full user journeys across the 3 reference screens’ flows |
| Load | k6 or Locust | Document pipeline under burst | Simulate month-end draw-season upload spike |
| Security | OWASP ZAP scan, manual pen-test before launch | — | Pre-pilot gate |

## 11. Sprint-by-Sprint Roadmap (24 Weeks, 2-Week Sprints)

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| 1 | 1–2 | Repo scaffold, CI skeleton, auth (WorkOS/Auth0 wired), org/user schema + RLS pattern proven on one table |
| 2 | 3–4 | Full base schema migrated (§3.1), Terraform base infra, staging environment live |
| 3 | 5–6 | Document ingestion (S3 presign, documents table), OCR (Textract) integration, pipeline_steps observability table |
| 4 | 7–8 | LLM extraction service (strict schemas), normalization, confidence gating, Needs_Review routing |
| 5 | 9–10 | Duplicate detection, split-screen review UI (frontend), manual verify endpoint end-to-end |
| 6 | 11–12 | Budget Truth (budget_lines/change_orders), Spend Truth posting from verified expenses, Four Truths API |
| 7 | 13–14 | Financial status snapshot engine, CPI/SPI/EAC, alert rules engine, AI explanation service |
| 8 | 15–16 | Portfolio dashboard UI (Four Truths tiles, spend breakdown charts, alerts panel) — image 2 parity |
| 9 | 17–18 | Draw module: pre-flight gate, draw creation, 4-step wizard UI — image 3 parity |
| 10 | 19–20 | Lender decision + child revision workflow, disbursement recording, funding reconciliation |
| 11 | 21–22 | Onboarding wizard (6 phases, auto-save draft) — image 1 parity; investor/portfolio reporting |
| 12 | 23–24 | Security hardening (OWASP pass, pen-test), load testing, exception-matrix QA (PRD §9), pilot launch with 1–2 real projects |

## 12. Team, Roles & RACI (Key Deliverables)

| Deliverable | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Schema + RLS | Backend Eng (DB owner) | Tech Lead | Security | Whole team |
| Document pipeline | AI/ML Eng + Backend Eng | Tech Lead | Domain SME (doc formats) | Product |
| Financial engine (Truths/EVM/alerts) | Backend Eng | Tech Lead | Domain SME (construction finance) | Product, QA |
| Frontend pages | Frontend Eng | Tech Lead | Design | Product |
| Infra/CI-CD | DevOps Eng | Tech Lead | Security | Whole team |
| Security review | Security-designated Eng/consultant | Tech Lead | — | Whole team |
| Pilot rollout | Product Manager | PM | Domain SME | Leadership |

Roles (recap from architecture plan): Tech Lead (1), Backend Eng (2–3), Frontend Eng (2), AI/ML Eng (1), DevOps Eng (1, can be shared/part-time), QA Eng (1), PM (1), Domain SME (advisory).

## 13. Cost Model (Illustrative — Confirm Against Current Vendor Pricing)

### 13.1 Build cost (24 weeks, 8 FTE average)

Rough order-of-magnitude engineering cost only (excludes overhead/benefits, varies heavily by region/market rate) — model this as FTE-weeks × loaded rate using your actual org’s rates; the structural inputs are: - 8 FTE average × 24 weeks = 192 person-weeks

### 13.2 Run cost (monthly, at pilot scale — a few active projects)

| Item | Est. monthly |
| --- | --- |
| RDS Postgres (multi-AZ, small instance) | $150–$400 |
| S3 storage + requests | $20–$100 (grows with document volume) |
| Textract (per-page pricing) | Scales with document volume — budget per-project estimate during pilot |
| Claude API (extraction + explanations) | Scales with document volume + AI-brief frequency — track token usage from sprint 4 onward to calibrate |
| SQS/Temporal, Redis, Fargate compute | $150–$500 |
| Auth provider (WorkOS/Auth0) | Free tier viable at pilot scale, then per-MAU |
| Monitoring (Sentry, Datadog) | $50–$300 |

Recommendation: instrument LLM token cost per document from day one (store token counts alongside pipeline_steps) — this is the one cost line that scales directly with usage and needs real pilot data to forecast accurately, rather than guessing upfront.

## 14. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| OCR/LLM extraction accuracy too low on messy real-world SOVs | Medium | High | Golden-set regression testing from Sprint 3 onward; keep human-review gate as permanent safety net, not a temporary crutch |
| Financial calculation bug (Truths/EVM) | Low likelihood, catastrophic if it happens | Critical | 100% branch coverage requirement on financial_engine/; no LLM in the math path (architectural, not just tested) |
| Multi-tenant data leak | Low | Critical | RLS enforced at DB layer + automated cross-tenant leak tests in CI on every migration |
| Textract/Claude API cost overrun at scale | Medium | Medium | Token/page usage tracked per document from Sprint 3; caching + text-not-image strategy (§5.4) |
| Lender-side rejection criteria mismatch (PRD §14 pending validation items) | Medium | Medium | Domain SME review before Sprint 9 (draw module); keep retainage/rejection logic config-driven, not hardcoded |
| Scope creep from V1.1 items (waterfall, bank feeds) pulled into V1 | Medium | Medium | PM enforces MoSCoW boundary; V1.1 backlog frozen until pilot feedback |
| Single Tech Lead bottleneck | Medium | Medium | Document architecture decisions (ADRs) as they’re made so knowledge isn’t siloed |

## 15. Definition of Done / Pilot-Launch Checklist

- ☐ All P0 requirements (PRD §6.1) implemented and covered by integration tests

- ☐ Every mutating endpoint role-gated and audit-logged

- ☐ RLS proven via automated cross-tenant test suite, passing in CI

- ☐ Financial engine unit tests at target coverage, all passing

- ☐ Document pipeline golden-set accuracy reviewed and accepted by Domain SME

- ☐ OWASP security scan + manual review completed, criticals resolved

- ☐ Load test passed for expected pilot document-upload volume

- ☐ Onboarding wizard resumes correctly from SETUP_DRAFT at every step (exact PRD §5.2 edge case)

- ☐ Click-to-source works end-to-end from any dashboard figure to the original S3 document

- ☐ Staging environment mirrors production infra; pilot data seeded and validated by Domain SME

- ☐ Runbook + on-call rotation defined for pilot support window

## 16. Post-V1 Roadmap (V1.1+)

- Investor waterfall / carrying-cost interest-erosion modeling (PRD §13)

- Direct bank feed integration (Plaid) replacing manual wire-slip entry

- Email ingestion adapter (P2)

- Multi-project executive portfolio rollup (P2)

- Move snapshot computation from synchronous to event-driven async if scale requires

- Evaluate splitting the Document Intelligence pipeline into its own deployable service if document volume growth outpaces the monolith

## Appendix: How This Plan Maps to the Reference Screens

- Image 1 (Auth/Intake gate) → §7 /login, §4.1 Auth Module, §11 Sprint 1 & 11

- Image 2 (Portfolio dashboard) → §7 /portfolio, §6 Financial engine, §4.9 endpoints, §11 Sprint 8

- Image 3 (Draw workspace, AI photo-matching) → §7 /projects/[id]/draws/[drawId], §4.8 Draws Module, §5 pipeline (confidence badges), §11 Sprint 9